## Chart
PROJECT TITLE | CMP Slurry Manufacturing
Goal: Finish most by RAPS | 2025-04-11 |  |  |  |  | Phase 1: Research |  |  |  |  | Phase 2: Implementation | [5 empty] | Phase 3: User Experience |  |  |  | Phase 4: Final Testing
Task Title | Task Owner | Status | Start | End | Half Weeks | 2025-03-02 | 2025-03-05 | 2025-03-09 | 2025-03-12 | 2025-03-16 | 2025-03-19 | 2025-03-23 | 2025-03-26 | 2025-03-30 | 2025-04-02 | 2025-04-06 | 2025-04-09 | 2025-04-13 | 2025-04-16 | 2025-04-20 | 2025-04-23 | 2025-04-27 | 2025-04-30 | 2025-05-04
Gantt Chart (Google Sheet) | All | Started | 2025-02-27 | 2025-03-02 | 1 | bar: 2025-03-02
Initial Design documents | All | Started | 2025-02-27 | 2025-03-05 | 2 | bar: 2025-03-02 to 2025-03-12
Research which language to use | Landon, Rosalia | Started | 2025-02-27 | 2025-03-02 | 1 | bar: 2025-03-02
Research CMP Slurry | All | Started | 2025-02-27 | 2025-03-02 | 1 | bar: 2025-03-02
Reseach how to get a website up and running from GitHub | Noah, Landon | Started | 2025-02-27 | 2025-03-02 | 1 | bar: 2025-03-02
Break down excel sheet into functionality | Jason, Billy, Rosalia | Started | 2025-02-27 | 2025-03-09 | 3 | bar: 2025-03-02 to 2025-03-09
Meet with end user again (before break) | All | Started | 2025-03-13 | 2025-03-16 | 1 | bar: 2025-03-12 to 2025-03-16
WritingHtml/CSS for simple site | Jason,Billy | Started | 2025-03-27 | 2025-04-05 | 3 | bar: 2025-03-30 to 2025-04-06
Writing JS for | Rosalia, Landon | Started | 2025-03-27 | 2025-04-05 | 3 | bar: 2025-03-30 to 2025-04-06
Meet with end user again (after break) | All | Not Started | 2025-04-04 | 2025-04-06 | 1 | bar: 2025-04-06
Input | Jason | Not Started | 2025-04-06 | 2025-04-20 | 4 | bar: 2025-04-09 to 2025-04-20
Graphics | Billy | Not Started | 2025-04-06 | 2025-04-20 | 4 | bar: 2025-04-09 to 2025-04-20
Formatting | Rosalia | Not Started | 2025-04-06 | 2025-04-20 | 4 | bar: 2025-04-09 to 2025-04-20
Demo Video | All | Not Started | 2025-04-13 | 2025-04-20 | 3
Testing interactions | All | Not Started | 2025-04-20 | 2025-05-04 | 4 | bar: 2025-04-23 to 2025-05-04

## Tasks
Task | How Long (# half weeks) | How Many People
Research | - | -
Gantt chart | 1 | 5
Research which language to use | 1 | 2025-02-03
Research CMP Slurry | 1 | 5
Break down excel sheet into functionality | 2025-02-03 | 2025-02-03
Reseach how to get a website up and running from GitHub | 1 | 2025-02-03
Meet with end user again (before break) | 1 | 5
Meet with end user again (after break) | 1
Implementation
Draft code for sheet 1 | 2 | 2025-02-03
Draft code for sheet 2 | 2 | 1
Draft code for sheet 3 | 2 | 1
Draft code for sheet 4 | 2 | 1
Draft code for sheet 5 | 2 | 1
Draft code for sheet 6 | 2 | 1
Draft code for sheet 7 | 2 | 1
Draft code for sheet 8 | 2 | 1
Draft code for sheet 9 | 2 | 1
Draft code for sheet 10 | 2 | 1
Draft code for sheet 11 | 2 | 1
Draft code for sheet 12 | 2 | 1
Draft code for sheet 13 | 2 | 1
Draft code for sheet 14 | 2 | 1
Draft code for sheet 15 | 2 | 1
Draft code for sheet 16 | 2 | 1
Draft code for sheet 17 | 2 | 1
Draft code for sheet 18 | 2 | 1
Draft code for sheet 19 | 2 | 1
User Experience
Input | 4 | 2025-02-03
Graphics | 4 | 2025-02-03
Formatting | 4 | 2025-02-03
Testing
Testing interactions | 4 | 5

## Plans
Plan A | Plan B | Plan C
an open source website that anyone could have access to, this would be the most useful for accessibility for research. | e an app you could download from github or partial functionality of the website, This would allow for partial use as well as accessibility. | an accessible script
Goal of April 11
Propose Plan for Updating GANTT chart each week: | Every Thursdays during class time
Key Risks to the success for this project: | Meeting up, stay on track, and skill limits